## RTM
Requirements Traceability Matrix - Project CCLT
School of Business & Economics - Thompson Rivers University
|  | Project Sponsor: | Milleni-X Transportation & Logistics
|  | Project Manager: | David Tran - T00691559
|  | Sponsor Representative: | John Ramblings, Terminal Manager
Req. # | Requirement ID | Component | Category | Requirement | Description | Date Created | Testing Dates | Priority | Approval Status | Testing Status | Pass / Fail | Notes
1 | 1-CFSLA-H | CFSLA | Functionality | CFS Lookahead functionality emulates the spreadsheet | Has at least the columns that exist in the spreadsheet: BOL/SSL, Vessel, Containers, Location, Commodity, Destination, Shipping number, JF reference, and comments | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS | [2024-01-16 DT] Some columns are broken up from the table to normalize and allow multivalue relationships without breaking normalization.
1.1 | 1.1-CFSLA-H | CFSLA | Functionality | CFS Lookahead can create new CFSLA entries | Can create a new entry. Entry is saved into database. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.1.1 | 1.1.1-CFSLA-H | CFSLA | Accessibility | CFS Lookahead has some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.1.2 | 1.1.2-CFSLA-H | CFSLA | Accessibility | CFS Lookahead returns error message if validation controls are not met. | Some indication / message in red. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.1.3 | 1.1.3-CFSLA-H | CFSLA | Accessibility | CFS Lookahead hides the window when the CANCEL button is clicked. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.1.4 | 1.1.4-CFSLA-H | CFSLA | Functionality | CFS Lookahead returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2 | 1.2-CFSLA-H | CFSLA | Accessibility | CFS Lookahead can view entries. | Clicking on the pencil icon will redirect to CFSLookahead/edit | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.1 | 1.2.1-CFSLA-H | CFSLA | Functionality | CFSLA Edit view displays information, including point of contact, business information, CFSLA entry, and all associated containers. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS | [2024-01-16 DT] Pulls data from other tables (ie. Contact table, Customer table, etc.) and uses the CustomerID as foreign key.
1.2.2 | 1.2.2-CFSLA-H | CFSLA | Functionality | CFSLA Update button can update the entry. | Adheres to formatting and data entry restriction / validation. See 1.1.1-CFSLA-H, 1.1.2-CFSLA-H | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.3 | 1.2.3-CFSLA-H | CFSLA | Accessibility | CFSLA Invoice Paid? toggles the "X" or "checkmark" when updated. | When the user adds or updates an entry and toggles the Invoice Paid? checkbox, if not checked will display an "X"; if checked, will display a "checkmark" to indicate invoice is paid. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.4 | 1.2.4-CFSLA-H | CFSLA | Accessibility | CFSLA Cancel button hides the Update window. | See 1.1.3-CFSLA-H | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.5 | 1.2.5-CFSLA-H | CFSLA | Accessibility | CFSLA Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.6 | 1.2.6-CFSLA-H | CFSLA | Functionality | CFSLA Confirm (Delete) button deletes the entry and all associated containers. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS | [2024-01-16 DT] Future enhancement - archive these records instead of permanently deleting them from database. Currently out of scope.
1.2.7 | 1.2.7-CFSLA-H | CFSLA | Functionality | CFSLA Add Unit creates a new container associated with the BOL (foreign key) | A new window pops up and prompts user to enter a Container number and saves it. Once saved and is successful, hides the popup and shows a green prompt. Refreshes screen in 3 seconds. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS | [2024-01-16 DT] Add some form validation here. Should be 4 alpha digits followed by 6 or 7 numbers. Will not use check digit to validate authenticity (out of scope)
1.2.8 | 1.2.8-CFSLA-H | CFSLA | Functionality | CFSLA Edit Unit allows the user to edit the container selected. | A new window pops up and prompts user to update and save the updated container number. Once updated and is successful, hides the popup and shows a green prompt. Refreshes screen in 3 seconds. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS | [2024-01-16 DT] Add some form validation here. Should be 4 alpha digits followed by 6 or 7 numbers. Will not use check digit to validate authenticity (out of scope)
1.2.9 | 1.2.9-CFSLA-H | CFSLA | Functionality | CFSLA Delete Unit allows the user to delete singular units. | A new window pops up and prompts user to review deletion. User confirms or cancels. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.10 | 1.2.10-CFSLA-H | CFSLA | Accessibility | CFSLA Cancel button hides the Delete window. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.2.11 | 1.2.11-CFSLA-H | CFSLA | Accessibility | CFSLA Confirm (Delete) button deletes the container. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
1.3 | 1.3-CFSLA-L | CFSLA | Functionality | Export to PDF | To determine requirements. | 2024-01-16 | 2024-02-23 | L | CANCELLED | Backlog | N/A
1.4 | 1.4-CFSLA-L | CFSLA | Functionality | Export to CSV | To determine requirements. | 2024-01-16 | 2024-02-23 | L | CANCELLED | Backlog | N/A
1.5.1 | 1.5.1-GENERAL-M | GENERAL | Ease of Use | Point of Contact - clicking the telephone number prompts user to call them (mobile. |  | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
1.5.2 | 1.5.2-GENERAL-M | GENERAL | Ease of Use | Point of Contact - clicking the email prompts the user to use an email client to email them. |  | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
2 | 2-DRAY-H | DRAY | Functionality | Drayage Cost Tracker functionality emulates the spreadsheet. | Has at least the columns that exist on the spreadsheet: Date, Trucking Provider Hired, # of Trucks Hired, Hours Worked, Containers Picked Up, Containers Returned, Customer, Product, JF reference, Other identifiers, and Amount. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.1 | 2.1-DRAY-H | DRAY | Functionality | Drayage Cost Tracker can create a new entry. | Can create a new entry. Entry is saved into database. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.1.1 | 2.1.1-DRAY-H | DRAY | Accessibility | Drayage Cost Tracker some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.1.2 | 2.1.2-DRAY-H | DRAY | Accessibility | Drayage Cost Tracker returns error message if validation controls are not met. | Some indication / message in red. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.1.3 | 2.1.3-DRAY-H | DRAY | Accessibility | Drayage Cost Tracker hides the window when the CANCEL button is clicked. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.1.4 | 2.1.4-DRAY-H | DRAY | Functionality | Drayage Cost Tracker returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.2 | 2.2-DRAY-H | DRAY | Accessibility | Drayage cost tracker can view entries. | Clicking on the pencil icon will redirect to DrayageCost/Edit | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.2.1 | 2.2.1-DRAY-H | DRAY | Functionality | Drayage Cost Tracker "View" view displays information, including point of contact, business information, and Drayage Cost Tracker entry. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.2.2 | 2.2.2-DRAY-M | DRAY | Accessibility | Trucker information is pulled from the Trucker ID going in and going out, and also pulls its hourly rate. |  | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
2.2.3 | 2.2.3-DRAY-M | DRAY | Accessibility | Based on the hourly rate, Drayage Metadata calculates the total cost of this Drayage Tracker, and the Cost Per Container. Used for KPI metrics. |  | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
2.3 | 2.3-DRAY-H | DRAY | Functionality | Drayage Cost Tracker Edit button can update the entry. | Adheres to formatting and data entry restriction / validation. See 2.1.1-DRAY-H, 2.1.2-DRAY-H | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.3.1 | 2.3.1-DRAY-H | DRAY | Functionality | Editing Dray Out Count, Dray In Count, Trucks Hired and Hours Worked will affect Drayage Metadata. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.3.2 | 2.3.2-DRAY-H | DRAY | Functionality | When edited (see 2.3.1-DRAY-H) Drayage Metadata will show updated Total Cost and Cost Per Container based on the business rules. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.3.3 | 2.3.3-DRAY-H | DRAY | Accessibility | Drayage Cost Tracker Cancel button hides the Edit window. | See 2.1.3-DRAY-H | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.3.4 | 2.3.4-DRAY-H | DRAY | Accessibility | Drayage Cost Tracker Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.3.5 | 2.3.5-DRAY-H | DRAY | Functionality | Drayage Cost TrackerConfirm (Delete) button deletes the entry. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
2.4 | 2.4-DRAY-L | DRAY | Ease of Use | Export to PDF | To determine requirements. | 2024-01-16 | 2024-02-23 | L | CANCELLED | Backlog | N/A
2.5 | 2.5-DRAY-L | DRAY | Ease of Use | Export to CSV | To determine requirements. | 2024-01-16 | 2024-02-23 | L | CANCELLED | Backlog | N/A
3 | 3-CONTRKR-H | CONTRKR | Functionality | Container Tracker functionality emulates the spreadsheet | Has at least the columns that exist in the spreadsheet: Date/ETA, Vessel, BOL, Container, Date In, Trucker In, Date Out, Trucker Out, Consignee, Size and Comments | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.1 | 3.1-CONTRKR-H | CONTRKR | Functionality | Container Tracker can create a new entry. | Can create a new entry. Entry is saved into database. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.1.1 | 3.1.1-CONTRKR-H | CONTRKR | Accessibility | Container Tracker some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.1.2 | 3.1.2-CONTRKR-H | CONTRKR | Accessibility | Container Tracker returns error message if validation controls are not met. | Some indication / message in red. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.1.3 | 3.1.3-CONTRKR-H | CONTRKR | Accessibility | Container Tracker hides the window when the CANCEL button is clicked. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.1.4 | 3.1.4-CONTRKR-H | CONTRKR | Functionality | Container Tracker returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.2 | 3.2-CONTRKR-H | CONTRKR | Accessibility | Drayage cost tracker can view entries. | Clicking on the pencil icon will redirect to ContainerTracker/Details | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.2.1 | 3.2.1-CONTRKR-H | CONTRKR | Functionality | Container Tracker "Details" view displays information, including point of contact, business information, and Container Tracker entry. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.2.2 | 3.2.2-CONTRKR-M | CONTRKR | Accessibility | Trucker information is pulled from the Trucker ID going in and going out, and also pulls its hourly rate. |  | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
3.3 | 3.3-CONTRKR-H | CONTRKR | Functionality | Drayage Cost Tracker Edit button can update the entry. | Adheres to formatting and data entry restriction / validation. See 3.1.1-CONTRKR-H, 3.1.2-CONTRKR-H | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.3.1 | 3.3.1-CONTRKR-H | CONTRKR | Functionality | Editing ETA, Date In and Date Out will affect Container Metadata. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.3.2 | 3.3.2-CONTRKR-M | CONTRKR | Functionality | Date Difference calculations (inclusive) are calculated between Carrier ETA and Gate In, Gate In and Gate Out, and Carrier ETA to Gate Out. | Grounded to Gate In KPI, Gate In to Gate Out KPI, Grounded to Gate Out KPI. | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
3.3.3 | 3.3.3-CONTRKR-M | CONTRKR | Ease of Use | Internal KPI benchmarks are hardcoded in. | These KPI benchmarks are used to measure Operational efficiency KPIs. See 3.3.2-CONTRKR-M. ETA-Gate In = 4 days, Gate In-Gate Out = 3 days, ETA-Gate Out = 7 days. | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
3.3.4 | 3.3.4-CONTRKR-M | CONTRKR | Accessibility | The Date Difference (see 3.3.2-CONTRKR-M) and Internal KPI benchmarks (see 3.3.3-CONTRKR-M) calculations are displayed in Container Metadata | Efficiency Formula = (Actual Metric - KPI Benchmark) / KPI Benchmark where lower is better (notated in Green with a down arrow). 0 is notated in yellow (par) and inefficient measurements are notated in red with an up arrow. | 2024-01-16 | 2024-02-23 | M | APPROVED | Completed | PASS
3.3.5 | 3.3.5-CONTRKR-H | CONTRKR | Accessibility | Container Tracker Cancel button hides the Edit window. | See 3.1.3-CONTRKR-H | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.3.6 | 3.3.6-CONTRKR-H | CONTRKR | Accessibility | Container Tracker Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.3.7 | 3.3.7-CONTRKR-H | CONTRKR | Functionality | Container Tracker Confirm (Delete) button deletes the entry and all associated containers. |  | 2024-01-16 | 2024-02-23 | H | APPROVED | Completed | PASS
3.4 | 3.4-CONTRKR-L | CONTRKR | Ease of Use | Export to PDF | To determine requirements. | 2024-01-16 | 2024-02-23 | L | CANCELLED | Backlog | N/A
3.5 | 3.5-CONTRKR-L | CONTRKR | Ease of Use | Export to CSV | To determine requirements. | 2024-01-16 | 2024-02-23 | L | CANCELLED | Backlog | N/A
4 | 4-TRKMGMT-H | TRKMGMT | Functionality | Trucker Management functionality emulates the spreadsheet. | Truckers are modeled based on their abbreviations, their company and their hourly rate. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.1 | 4.1-TRKMGMT-H | TRKMGMT | Functionality | Trucker Management can create a new entry. | Can create a new entry. Entry is saved into database. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.1.1 | 4.1.1-TRKMGMT-H | TRKMGMT | Accessibility | Trucker Management some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.1.2 | 4.1.2-TRKMGMT-H | TRKMGMT | Accessibility | Trucker Management returns error message if validation controls are not met. | Some indication / message in red. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.1.3 | 4.1.3-TRKMGMT-H | TRKMGMT | Functionality | Trucker Management hides the window when the CANCEL button is clicked. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.1.4 | 4.1.4-TRKMGMT-H | TRKMGMT | Functionality | Trucker Management returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.2 | 4.2-TRKMGMT-H | TRKMGMT | Accessibility | Trucker Management can view entries. | Clicking on the magnifying icon will redirect to Truckers/details | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.2.1 | 4.2.1-TRKMGMT-H | TRKMGMT | Functionality | Trucker Management "View" view displays information, including point of contact, business information, and Trucker Management entry. | If the point of contact does not exist, all POC information are set to N/A | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.3.1 | 4.3.1-TRKMGMT-H | TRKMGMT | Functionality | Trucker Management Edit button can update the entry. | Adheres to formatting and data entry restriction / validation. See 4.1.1-TRKMGMT-H, 4.1.2-TRKMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.3.4 | 4.3.4-TRKMGMT-H | TRKMGMT | Accessibility | Trucker Management Cancel button hides the Edit window. | See 4.1.3-TRKMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.3.5 | 4.3.5-TRKMGMT-H | TRKMGMT | Accessibility | Trucker Management Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
4.3.6 | 4.3.6-TRKMGMT-H | TRKMGMT | Functionality | Trucker ManagementConfirm (Delete) button deletes the entry. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5 | 5-CUSMGMT-H | CUSMGMT | Functionality | Customer Management functionality emulates the spreadsheet. | Truckers are modeled based on their abbreviations, their company and their hourly rate. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.1 | 5.1-CUSMGMT-H | CUSMGMT | Functionality | Customer Management can create a new entry. | Can create a new entry. Entry is saved into database. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.1.1 | 5.1.1-CUSMGMT-H | CUSMGMT | Accessibility | Customer Management some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.1.2 | 5.1.2-CUSMGMT-H | CUSMGMT | Accessibility | Customer Management returns error message if validation controls are not met. | Some indication / message in red. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.1.3 | 5.1.3-CUSMGMT-H | CUSMGMT | Accessibility | Customer Management hides the window when the CANCEL button is clicked. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.1.4 | 5.1.4-CUSMGMT-H | CUSMGMT | Functionality | Customer Management returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.2 | 5.2-CUSMGMT-H | CUSMGMT | Accessibility | Customer Management can view entries. | Clicking on the magnifying icon will redirect to Truckers/details | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.2.1 | 5.2.1-CUSMGMT-H | CUSMGMT | Functionality | Customer Management "View" view displays information, including point of contact, business information, and Customer Management entry. | If the point of contact does not exist, all POC information are set to N/A | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.3.1 | 5.3.1-CUSMGMT-H | CUSMGMT | Functionality | Customer Management Edit button can update the entry. | Adheres to formatting and data entry restriction / validation. See 5.1.1-CUSMGMT-H, 5.1.2-CUSMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.3.4 | 5.3.4-CUSMGMT-H | CUSMGMT | Accessibility | Customer Management Cancel button hides the Edit window. | See 5.1.3-CUSMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.3.5 | 5.3.5-CUSMGMT-H | CUSMGMT | Accessibility | Customer Management Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
5.3.6 | 5.3.6-CUSMGMT-H | CUSMGMT | Functionality | Customer ManagementConfirm (Delete) button deletes the entry. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6 | 6-SSLMGMT-H | SSLMGMT | Functionality | Line Operator Management functionality emulates the spreadsheet. | Line Operators are modeled based on their abbreviations, their company and their hourly rate. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.1 | 6.1-SSLMGMT-H | SSLMGMT | Functionality | Line Operator Management can create a new entry. | Can create a new entry. Entry is saved into database. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.1.1 | 6.1.1-SSLMGMT-H | SSLMGMT | Accessibility | Line Operator Management some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.1.2 | 6.1.2-SSLMGMT-H | SSLMGMT | Accessibility | Line Operator Management returns error message if validation controls are not met. | Some indication / message in red. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.1.3 | 6.1.3-SSLMGMT-H | SSLMGMT | Accessibility | Line Operator Management hides the window when the CANCEL button is clicked. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.1.4 | 6.1.4-SSLMGMT-H | SSLMGMT | Functionality | Line Operator Management returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.2 | 6.2-SSLMGMT-H | SSLMGMT | Accessibility | Line Operator Management can view entries. | Clicking on the magnifying icon will redirect to LineOperator/details | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.2.1 | 6.2.1-SSLMGMT-H | SSLMGMT | Functionality | Line Operator Management "View" view displays information, including point of contact, business information, and Line Operator Management entry. | If the point of contact does not exist, all POC information are set to N/A | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.3.1 | 6.3.1-SSLMGMT-H | SSLMGMT | Functionality | Line Operator Management Edit button can update the entry. | Adheres to formatting and data entry restriction / validation. See 6.1.1-SSLMGMT-H, 6.1.2-SSLMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.3.4 | 6.3.4-SSLMGMT-H | SSLMGMT | Accessibility | Line Operator Management Cancel button hides the Edit window. | See 6.1.3-SSLMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.3.5 | 6.3.5-SSLMGMT-H | SSLMGMT | Accessibility | Line Operator Management Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
6.3.6 | 6.3.6-SSLMGMT-H | SSLMGMT | Functionality | Line Operator ManagementConfirm (Delete) button deletes the entry. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7 | 7-POCMGMT-H | POCMGMT | Functionality | Point of Contact Management functionality emulates the spreadsheet. | Point of Contacts are modeled based on their abbreviations, their company and their hourly rate. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.1 | 7.1-POCMGMT-H | POCMGMT | Functionality | Point of Contact Management can create a new entry. | Can create a new entry. Entry is saved into database. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.1.1 | 7.1.1-POCMGMT-H | POCMGMT | Accessibility | Point of Contact Management some validation controls. | Mandatory fields are marked and checked. Non-mandatory fields are not checked. All fields must adhere to formatting. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.1.2 | 7.1.2-POCMGMT-H | POCMGMT | Accessibility | Point of Contact Management returns error message if validation controls are not met. | Some indication / message in red. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.1.3 | 7.1.3-POCMGMT-H | POCMGMT | Accessibility | Point of Contact Management hides the window when the CANCEL button is clicked. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.1.4 | 7.1.4-POCMGMT-H | POCMGMT | Functionality | Point of Contact Management returns to the Datatables view when creating a new entry. | No errors. Submitted into database successfully. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.2 | 7.2-POCMGMT-H | POCMGMT | Accessibility | Point of Contact Management can view entries. | Clicking on the magnifying icon will redirect to LineOperator/details | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.2.1 | 7.2.1-POCMGMT-H | POCMGMT | Functionality | Point of Contact Management "View" view displays information, including point of contact, business information, and Point of Contact Management entry. | If the point of contact does not exist, all POC information are set to N/A | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.3.1 | 7.3.1-POCMGMT-H | POCMGMT | Functionality | Point of Contact Management Edit button can update the entry. | Adheres to formatting and data entry restriction / validation. See 7.1.1-POCMGMT-H, 7.1.2-POCMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.3.4 | 7.3.4-POCMGMT-H | POCMGMT | Accessibility | Point of Contact Management Cancel button hides the Edit window. | See 7.1.3-POCMGMT-H | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.3.5 | 7.3.5-POCMGMT-H | POCMGMT | Accessibility | Point of Contact Management Delete button prompts user to review before deleting. | Shows all of the entry's information and all associated containers. All records will be deleted. | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
7.3.6 | 7.3.6-POCMGMT-H | POCMGMT | Functionality | Point of Contact Management Confirm (Delete) button deletes the entry. |  | 2024-02-19 | 2024-02-23 | H | APPROVED | Completed | PASS
8 | 8-NAVIGATION-M | NAVIGATION | Accessibility | Navigation bar availabe at the top of each page |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
8.1 | 8.1-NAVIGATION-M | NAVIGATION | Accessibility | Navigation bar have buttons for each of the application components | Components are: Home page, CFS Lookahead, Container Tracker, Drayage Cost Tracker, Line Operator Mgmt, Customer Mgmt, Trucker Mgmt and POC Mgmt. | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
8.2 | 8.2-NAVIGATION-M | NAVIGATION | Functionality | Each button on the navigation bar redirects to the proper application component. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
8.3 | 8.3-NAVIGATION-M | NAVIGATION | Functionality | Each button on the navigation bar redirects to the proper application component when in the details page of any application component. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
8.4 | 8.4-NAVIGATION-M | NAVIGATION | Accessibility | On cursor hover, the navigation bar responds with a slight change in the button colour to provide indication that it is being interacted with. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
8.5 | 8.5-NAVIGATION-M | NAVIGATION | Accessibility | On the home page, there is a button that represents each of the application components. | Components are: CFS Lookahead, Container Tracker, Drayage Cost Tracker, Line Operator Mgmt, Customer Mgmt, Trucker Mgmt and POC Mgmt. | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
8.6 | 8.6-NAVIGATION-M | NAVIGATION | Accessibility | On hover, each button grows slightly to indicate the button is being interacted with. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.1 | 9.1-GENERAL-M | GENERAL | Accessibility | Application is accessible through a public domain |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.2 | 9.2-GENERAL-M | GENERAL | Accessibility | Each of the datatables can be searchable in the Search input field on the top right corner of each datatable. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.3 | 9.3-GENERAL-M | GENERAL | Functionality | The search input field at the top right corner of each datatable is able to comprehensively search all columns of the datatable. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.4 | 9.4-GENERAL-M | GENERAL | Functionality | The search input field, when values are entered, searches and filters the datatable. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.5 | 9.5-GENERAL-M | GENERAL | Accessibility | When the datatable is searched and filtered, the table responds with a truncated datatable for easier reading. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.6 | 9.6-GENERAL-M | GENERAL | Accessibility | Each datatable column (except for the Action column) has a search field specific to that column. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.7 | 9.7-GENERAL-M | GENERAL | Functionality | Each datatable column can sort from lowest to highest, etc. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.8 | 9.8-GENERAL-M | GENERAL | Functionality | Each datatable column search is mutually exclusive to other columns |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.9 | 9.9-GENERAL-M | GENERAL | Functionality | When a column is searched, the datatable respons with a truncated datatable for easier reading. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.1 | 9.1-GENERAL-M | GENERAL | Functionality | When multiple columns are searched, the datatable recursively searches through the dataset and filters based on all of the criteria in each column. |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.11 | 9.11-GENERAL-M | GENERAL | Accessibility | There is a selection of the number of rows to be presented to the user. | The user can select [25, 50, 100, 250]. Default for all applicatons is 25. | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.12 | 9.12-GENERAL-M | GENERAL | Functionality | When the number of rows is changed by the user, the datatables update responsively and accordingly to the new value. | Pagination numbers also change based on the dataset divided by the number of rows presented. | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.13 | 9.13-GENERAL-M | GENERAL | Accessibility | There is pagination available at the bottom of each datatable |  | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
9.14 | 9.14-GENERAL-M | GENERAL | Accessibility | Pagination includes different ways to navigate. | Includes previous, next, page number, first and last. | 2024-02-19 | 2024-02-23 | M | APPROVED | Completed | PASS
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--
--